UNIVERSITY OF GHANA — DEPARTMENT OF COMPUTER SCIENCE

CSCD602: Advanced Software Engineering — Individual Project-Based Examination

Software Effort Estimation

Volunteer Shift Scheduler

| Field | Detail |
| --- | --- |
| Student Name | Samuel Owusu Ampadu |
| Student ID | 22424245 |
| Technique Applied | Use Case Points (UCP) |
| Date | 13 August 2026 |

# 1. Technique Selection and Justification

Use Case Points (UCP) was selected as the effort estimation technique for this project, in preference to COCOMO II, Function Point Analysis, and Story Points, for the following reasons:

- UCP estimates directly from use cases and actors, which the SRS already defines — no additional artefact is needed before estimation can begin.

- COCOMO II requires a KLOC (lines-of-code) size proxy, which cannot be honestly estimated before any code exists; UCP avoids this circularity.

- Function Point Analysis requires classifying every input, output, and file against 14 General System Characteristics — a heavier process than the exam's Phase 1 time budget (Hours 0–4) justifies.

- Story Points require a team velocity baseline from prior sprints, which does not exist for a solo, one-off 48-hour build.

- UCP is specifically calibrated for object-oriented, GUI-driven systems, matching this project's React/Supabase architecture and actor-based use cases.

# 2. Use Case Points Calculation

## 2.1 Unadjusted Use Case Weight (UUCW)

Only Must-have use cases (see SRS Section 3) are scored, since Should/Could items are not guaranteed within scope.

| Use Case | Complexity | Weight |
| --- | --- | --- |
| Register / Log In (Volunteer) | Simple | 5 |
| Log In (Coordinator) | Simple | 5 |
| Create Shift | Average | 10 |
| View Open Shifts | Simple | 5 |
| Sign Up for Shift (capacity + overlap check) | Complex | 15 |
| Cancel Sign-Up | Simple | 5 |
| View Roster | Average | 10 |
| Mark Attendance | Simple | 5 |

UUCW = 5+5+10+5+15+5+10+5 = 60

## 2.2 Unadjusted Actor Weight (UAW)

Both actors (Volunteer, Coordinator) interact through a GUI and are classified as Complex (weight 3 each).

UAW = 2 actors × 3 = 6      UUCP = UUCW + UAW = 60 + 6 = 66

## 2.3 Technical Complexity Factor (TCF)

| ID | Factor | Weight | Rating (0–5) | Value |
| --- | --- | --- | --- | --- |
| TF1 | Distributed system | 2 | 1 | 2 |
| TF2 | Response time / performance objectives | 1 | 3 | 3 |
| TF3 | End-user efficiency | 1 | 4 | 4 |
| TF4 | Complex internal processing | 1 | 3 | 3 |
| TF5 | Code reusability | 1 | 1 | 1 |
| TF6 | Easy to install | 0.5 | 5 | 2.5 |
| TF7 | Easy to use | 0.5 | 4 | 2 |
| TF8 | Portability | 2 | 3 | 6 |
| TF9 | Easy to change | 1 | 3 | 3 |
| TF10 | Concurrent use | 1 | 2 | 2 |
| TF11 | Security features | 1 | 4 | 4 |
| TF12 | Third-party access | 1 | 0 | 0 |
| TF13 | Special user training required | 1 | 1 | 1 |

ΣTFactor = 33.5      TCF = 0.6 + (0.01 × 33.5) = 0.935

## 2.4 Environmental Factor (EF)

| ID | Factor | Weight | Rating (0–5) | Value |
| --- | --- | --- | --- | --- |
| EF1 | Familiarity with UCP / use-case modelling | 1.5 | 3 | 4.5 |
| EF2 | Application (domain) experience | 0.5 | 4 | 2 |
| EF3 | Object-oriented experience | 1 | 4 | 4 |
| EF4 | Lead analyst capability | 0.5 | 4 | 2 |
| EF5 | Motivation | 1 | 5 | 5 |
| EF6 | Stable requirements | 2 | 3 | 6 |
| EF7 | Part-time staff (negative factor) | -1 | 0 | 0 |
| EF8 | Difficult programming language (negative factor) | -1 | 1 | -1 |

ΣEFactor = 22.5      EF = 1.4 − (0.03 × 22.5) = 0.725

## 2.5 Adjusted Use Case Points

Adjusted UCP = UUCP × TCF × EF = 66 × 0.935 × 0.725 ≈ 45 UCP

# 3. Theoretical Effort vs. the 48-Hour Time-Box

At the standard industry ratio of 20 person-hours per UCP, 45 Adjusted UCP implies approximately 900 person-hours of effort — a figure calibrated for professional software delivery, including formal QA cycles, team coordination overhead, and full non-functional rigor.

This is obviously infeasible within 48 hours, and that gap is the central input to scoping this project: it is the quantitative justification for building only the Must-have requirements and explicitly deferring every Should- and Could-have item (see Section 6, Influence on Scope).

# 4. Practical Implementation Budget

The 20 hours/UCP industry ratio is not used directly for the build plan, because it embeds professional-process overhead (formal documentation cycles, team communication, extended QA) that does not apply to a solo developer already fluent in the chosen stack. Instead, each Must-have use case is budgeted individually by expert judgement, cross-checked against its UCP weight:

| Use Case | UCP Weight | Est. Hours |
| --- | --- | --- |
| Register / Log In (Volunteer) | 5 | 1.5 |
| Log In (Coordinator) | 5 | 1.0 |
| Create Shift | 10 | 2.5 |
| View Open Shifts | 5 | 1.5 |
| Sign Up for Shift (capacity + overlap check) | 15 | 5.0 |
| Cancel Sign-Up | 5 | 1.5 |
| View Roster | 10 | 2.0 |
| Mark Attendance | 5 | 1.5 |
| Project scaffolding, Supabase wiring, base styling | — | 1.5 |
| Total |  | 18.0 |

# 5. Estimated Development Duration

The 18-hour implementation budget from Section 4 is allocated within the wider 48-hour lifecycle as follows:

| Phase | Activity | Window | Hours |
| --- | --- | --- | --- |
| 1 | Planning & Requirements | Hours 0–4 | 4 |
| 2 | Analysis & Design | Hours 4–8 | 4 |
| 3 | Implementation | Hours 8–26 | 18 |
| 4 | Testing & Refinement | Hours 26–32 | 6 |
| 5 | Deployment | Hours 32–36 | 4 |
| 6 | Documentation & Submission | Hours 36–48 | 12 |
| Total |  |  | 48 |

# 6. Assumptions, Constraints, and Influence on Scope

## 6.1 Assumptions

- The developer's existing familiarity with React, Supabase, and Vercel (from prior coursework) is representative of actual delivery speed.

- No significant tooling, environment, or account-setup failures occur during the 48-hour window.

- Requirements, once locked at the end of Phase 1, remain stable for the remainder of the build.

## 6.2 Constraints

- Total elapsed time is fixed at 48 hours, including planning, design, testing, deployment, and documentation — not just coding.

- The work must be completed individually, with no code, SRS, or design collaboration with other students.

- The deployed application must remain accessible for grading after submission.

## 6.3 Influence on Scope

The approximately 20x gap between the theoretical UCP-based effort (≈900 hours) and the available time directly drove the MoSCoW prioritisation in the SRS: only the eight Must-have use cases (FR-01–FR-08) are committed to the build plan. Should-have items (FR-09–FR-11) are attempted only if the Section 4 budget is not exceeded, and Could-have items (FR-12–FR-13) are documented as future work rather than built, consistent with the Technical Debt Plan.